## Objective
Purpose | Target Users
Ensure the VWO Login Dashboard provides secure, intuitive, and eﬃcient authentication. | Primary: digital marketers, product managers, UX designers, developers. Secondary: enterprise teams, CRO specialists, data analysts.

## Scope
Features to be tested | Types of testing
Email/password auth, Remember Me, session management, password reset, 2FA, SSO (SAML/OAuth), responsive UI, accessibility (WCAG 2.1 AA), load time optimizations. | Manual functional, automated regression, performance/load, security, accessibility testing.

## Inclusions
Overview | Test Objectives
Core authentication, Enhanced UX (mobile optimization, accessibility), Enterprise features (SSO, advanced security, analytics). | Verify authentication correctness, session management, password recovery, performance targets (sub-2-second load), and security requirements.

## Exclusions
Out of scope | Details
Features not listed in PRD (e.g., non-login platform areas, specific backend admin APIs). | Any features outside the login dashboard boundaries.

## Test Environments
Operating Systems | Browsers / Form Factors
Windows 10, macOS, Linux, Mobile OS (for responsive design). | Chrome, Firefox, Edge, Safari.

## Defect Reporting Procedure
Criteria | Steps
Deviation from PRD requirements (functional, security, performance, accessibility). | Log defects in JIRA; include reproduction steps, screenshots/logs.

## Test Strategy
Design Techniques | Procedure
Equivalence Class Partitioning; Boundary Value Analysis; Use Case Testing; Error Guessing; Exploratory Testing. | Smoke testing -> in-depth functional/regression -> cross-environment compatibility; security/pen tests and load tests per PRD.

## Test Schedule
Tasks | Details
Phase 1: Core Authentication. Phase 2: Enhanced UX. Phase 3: Enterprise Features. Includes Test plan creation, test case design, execution, and report submission. | Timelines to be strictly aligned with project milestones.

## Test Deliverables
Deliverables | Description
Test plan, test cases/scripts, execution reports, defect reports, performance and accessibility reports. | Documents provided at various stages of the testing lifecycle.

## Entry and Exit Criteria
Entry Criteria | Exit Criteria
PRD received. Test environment and test data ready. | 95%+ login success rate, sub-2-second load time, 0 successful brute force attacks, 100% compliance with security audit requirements, reduced support volume by 20%.

## Tools
Tools | Purpose
JIRA (bug tracking); screenshot/snipping tools; Word/Excel for documentation. | Required for test creation, execution, and defect logging.

## Risks and Mitigations
Risks | Mitigations
Security vulnerabilities, Performance issues under heavy load. | Regular security audits and pen testing, Auto-scaling infrastructure, Real-time performance monitoring.