## Sheet1
Section | Title | Description
1. Objective | Test Plan for AB Testing Website | This document outlines the test plan for the AB Testing website (app.vwo.com), ensuring that all features and functionalities work as expected for the target audience.
2. Scope | Features, Types of Testing, Environments, and Evaluation Criteria | Features to be tested: Home page, About page, Pricing page, Sign-up page, and Login page. Types of testing: Manual testing, automated testing, performance testing, and accessibility testing. Environments: Different browsers, operating systems, and devices. Evaluation criteria: Number of defects found, time taken to complete testing, and user satisfaction ratings.
3. Inclusions | Test Plan Overview, Test Objectives, and Exclusions | Introduction: Overview of the test plan, including purpose, scope, and goals. Test Objectives: Identify defects and improve user experience. Achieve a certain level of performance and accessibility. Exclusions: Features or components that are not relevant to the target audience or are out of scope.
4. Exclusions | List of Features or Components Out of Scope | Features or components that are not relevant to the target audience or are out of scope.
5. Test Environments | Operating Systems, Browsers, Devices, Network Connectivity, and Hardware/Software Requirements | Operating Systems: Windows 10, macOS, Linux. Browsers: Google Chrome, Mozilla Firefox, Microsoft Edge. Devices: Desktop computers, laptops, tablets, smartphones. Network Connectivity: Wi-Fi, cellular, wired connections. Hardware/Software Requirements: Specific processor, memory, storage capacity, etc. Security Protocols: Passwords, tokens, certificates. Access Permissions: Roles for team members such as testers, developers, stakeholders.
6. Defect Reporting Procedure | Criteria for Identifying Defects, Steps for Reporting Defects, and Triage and Prioritization | Criteria for identifying defects: Deviation from requirements, user experience issues, technical errors. Steps for reporting defects: Using a designated template, providing detailed reproduction steps, attaching screenshots or logs. Triage and prioritization: Assigning severity and priority levels, assigning defects to appropriate team members. Tracking tools: Defect tracking software or project management tool. Roles and responsibilities: Testers, developers, test lead, etc. Communication channels: Updating stakeholders on progress and status of defects. Metrics: Number of defects found, time taken to resolve, percentage of defects fixed.
7. Test Strategy | Test Scenarios and Test Cases Creation, Testing Procedure, and Best Practices | Test Scenarios and Test Cases Creation: Equivalence Class Partition, Boundary Value Analysis, Decision Table Testing, State Transition Testing, Use Case Testing. Additional methods: Error Guessing, Exploratory Testing. Testing Procedure: Smoke Testing, In-depth Testing, Multiple environments, Defect Reporting. Best Practices: Context Driven Testing, Shift Left Testing, Exploratory Testing, End to End Flow Testing.
8. Test Schedule | Tasks and Time Duration, Dates, and Roles and Responsibilities | Tasks and Time Duration: Creating test plan, test case creation, test case execution, summary reports submission. Dates: Specify the timeline for each task. Roles and Responsibilities: Test lead, testers, developers, etc.
9. Test Deliverables | Entry and Exit Criteria, Requirement Analysis, Test Execution, and Test Closure | Entry and Exit Criteria: Requirement Analysis, Test Execution, Test Closure. Requirement Analysis: Entry: Receiving Requirements Documents. Exit: Understanding and clarifying requirements. Test Execution: Entry: Signed-off Test Scenarios and Test Cases, Application ready for testing. Exit: Test Case Reports, Defect Reports ready. Test Closure: Entry: Test Case Reports, Defect Reports ready. Exit: Test Summary Reports.
10. Tools | List of Tools Used for Testing | JIRA Bug Tracking Tool, Mind map Tool, Snipping Screenshot Tool, Word and Excel documents
11. Risks and Mitigations | List of Possible Risks and Mitigations | Non-Availability of a Resource, Build URL not working, Less time for Testing. Mitigations: Backup Resource Planning, working on other tasks, ramping up resources dynamically.
12. Approvals | Documents Required for Client Approval | Test