## Objective
Purpose | Ensure the VWO Login Dashboard provides secure, accessible, performant, and correct authentication and onboarding flows for the target users listed in the PRD.
Target Users | See Verified Facts sheet.

## Scope
Features to be tested | Email/password auth; Remember Me; session management; password reset; optional MFA; SSO (SAML/OAuth) paths; validation behaviors; responsive UI; accessibility features; security behaviors; analytics emission to core dashboard.
Types of testing | Manual functional, automated regression, performance/load, security (pen-tests), accessibility (WCAG 2.1 AA), compatibility.
Environments | OS and browsers per user template (Windows 10, macOS, Linux; Chrome, Firefox, Edge); devices: desktop/laptop/tablet/smartphone. Exact versions not provided.
Evaluation criteria | Defect counts; time to complete testing; user satisfaction; KPIs from PRD (page load <2s, login success rate >=95%).

## Inclusions
Overview | Overview, purpose, scope, goals as extracted from PRD.
Test Objectives | Verify authentication correctness, session management, password recovery, accessibility per WCAG 2.1 AA, performance targets, and security requirements per PRD.

## Exclusions
Out of scope | Features not listed in PRD (e.g., non-login platform areas). Specific backend admin APIs are out of scope unless provided).

## Test Environments
Operating Systems | Windows 10; macOS; Linux (exact versions not provided).
Browsers | Google Chrome; Mozilla Firefox; Microsoft Edge (versions not provided).
Devices | Desktop, laptop, tablet, smartphone.
Network | Wi-Fi, cellular, wired — simulate standard connection to validate <2s load target.
Security Protocols | HTTPS/TLS enforcement required (exact TLS versions not provided).

## Defect Reporting Procedure
Criteria | Deviation from PRD requirements (functional, security, performance, accessibility)
Steps | Log defects in tracking tool (e.g., JIRA); include reproduction steps, screenshots/logs
Triage | Assign severity/priority; test lead triages; developers assigned for fixes.

## Test Strategy
Design Techniques | Equivalence Class Partitioning; Boundary Value Analysis; Decision Table; State Transition; Use Case Testing; Error Guessing; Exploratory Testing.
Procedure | Smoke testing -> in-depth functional/regression -> cross-environment compatibility; security/pen tests and load tests per PRD; accessibility checks.
Best Practices | Shift-left testing; context-driven testing; exploratory testing; end-to-end flow testing.

## Test Schedule
Tasks | Test plan creation; test case design; test execution; report submission.
Dates | Insufficient information to determine specific dates or timeline.

## Test Deliverables
Deliverables | Test plan; test cases/scripts; execution reports; defect reports; performance and accessibility reports.

## Entry and Exit Criteria
Requirement Analysis Entry | PRD and requirements documents received.
Requirement Analysis Exit | Requirements clarified and test plan approved.
Test Execution Entry | Signed-off test scenarios and test cases; application build ready.
Test Execution Exit | Test case execution completed; defects logged; regression criteria met.

## Tools
Tools | JIRA (bug tracking); screenshot/snipping tools; Word/Excel for documentation. Specific automation/perf/security tools not provided.

## Risks and Mitigations
Risks | Non-availability of resources; build/URL not working; insufficient time; security/compliance gaps if controls missing; performance issues if CDN/scaling not configured.
Mitigations | Backup resource planning; parallel tasks; security audits and monitoring as PRD indicates.

## Approvals
Approval Documents | Test Plan; Test Scenarios; Test Cases; Test Reports.

## Verified Facts
Document | VWO Login Dashboard (app.vwo.com)
Product Vision | Secure, intuitive, efficient login experience connecting users to VWO platform.
Target Users | Digital marketers; product managers; UX designers; developers; enterprise teams; CRO specialists; data analysts.
Business Objectives | Secure access; minimize login friction; support enterprise security/compliance; facilitate onboarding.

## Missing Unknown Information
Item | API documentation / authentication endpoint contracts (URLs, request/response schemas, status codes).
Item | Test accounts / credentials / test data for authentication flows.
Item | Exact password complexity rules and hashing algorithm details.
Item | Specific SSO and MFA configuration details.
Item | Exact session timeout values and rate-limiting thresholds.
Item | UI mockups, exact copy for labels and error messages.
Item | Browser/OS/version matrix and device model list.
Item | Timeline / schedule and named owners for tasks.